## Tabelle1
Projectplan
Kick-Off
| Initialisation | Projectplan
| Projectplan | Literature review | Results of literature
|  | Review | POC remove lesions 2D |  | Result of POC
|  | Literature | Setup preprocessing |  | POC add lesions 2D |  | Result of POC
|  |  | Setup training pipeline |  | Setup preprocessing |  | POC remove lesions 3D |  | Result of POC
|  |  | Uncond. model Refill |  | Setup training pipeline |  | Setup preprocessing |  | POC add lesions 3D |  | Result of POC
|  |  | Cond. model DDPM / SD |  | Trying different models |  | Setup training pipeline |  | Setup preprocessing |  | Conception | Approved concepts
[7 empty] | Trying different models |  | Setup training pipeline |  | Dataset | Implementation |  |  | Final model
[9 empty] | Trying different models |  | Preprocessing | Setup preprocessing |  |  | Draft report | Draft
[11 empty] | Training | Setup training pipeline |  |  | Write draft | Add. Datasets | Further results
[11 empty] | Evaluation | Train model |  |  |  | Seizures | Result analysis |  | Interpretation of results
[11 empty] | Define model | Evaluate and adjust training |  |  |  | Epilepsy | Final results |  | Finalisation |  |  |  | Final report
[11 empty] | Approval | [5 empty] | Interpretation of results |  | Write Report |  |  |  | Reserves |  |  |  | Report submitted
[17 empty] | Conclusions | [9 empty] | Thesis presentation |  |  | Thesis completion
Outlook
| Cweek 10 | Cweek 11 | Cweek 12 | Cweek 13 | Cweek 14 | Cweek 15 | Cweek 16 | Cweek 17 | Cweek 18 | Cweek 19 | Cweek 20 | Cweek 21 | Cweek 22 | Cweek 23 | Cweek 24 | Cweek 25 | Cweek 26 | Cweek 27 | Cweek 28 | Cweek 29 | Cweek 30 | Cweek 31 | Cweek 32 | Cweek 33 | Cweek 34 | Cweek 35 | Cweek 36 | Cweek 37 | Cweek 38
| 04.03. | 11.03. | 18.03. | 25.03. | 01.04. | 08.04. | 15.04. | 22.04. | 29.04. | 06.05. | 13.05. | 20.05. | 27.05. | 03.06. | 10.06. | 17.06. | 24.06. | 01.07. | 08.07. | 15.07. | 22.07. | 29.07. | 05.08. | 12.08. | 19.08. | 26.08. | 02.09. | 09.09. | 16.09.
|  |  |  | 28.03.-22.04. Holiday Richard |  |  |  |  | 01.05. Last day Stefano | [16 empty] | 31.08. submission